## All Tasks
Task Heading | Task Description | Status | Source | Why We're Doing This | Growth Pillar | SPOC | Priority | Go Live | Remarks
Check Caption on Amazon | Verify if the specified range is available on Amazon to ensure the caption is accurate. | open | Chat ¦ with Aman | Accurate product information is crucial for customer satisfaction and trust. | Operations | Aman | Medium
Create Bundle Link | Create a link for the bundle that is missing images, and share it with Anchit. | open | Chat ¦ with Manisha | Missing images are blocking the bundle's visibility, and having a link will help Anchit move forward. | Operations | Manisha | High
Work with Aman on Klaviyo Integration | Collaborate with Aman to figure out Klaviyo integration and its requirements. | open | Chat ¦ with Anchit Tandon | Klaviyo integration is crucial for retention via email/SMS/WhatsApp. | Retention | Anchit Tandon | High
Review Mailer Creation Document | Review the document with feedbacks for mailer creation and ensure it's ready for today. | open | Chat ¦ with Anchit | To ensure the mailer creation is done correctly and on time. | Operations | Anchit | High | Today
Send 1st mailer | Send the first mailer as per the calendar sheet to subscribers. | open | Chat ¦ with Aman | To maintain a consistent gifting calendar and keep subscribers engaged. | Retention | Aman | Medium | As per calendar sheet
Fix Product Page Alignment | Ensure that the product descriptions are evenly spaced and do not break the alignment on the product page. | open | Chat ¦ with Aman | A cluttered product page can negatively impact user experience and conversion rates. | Conversion | Aman | High
Correct Grammar in Product Selection | Review and correct the grammar in the product selection percentage (currently 58%) to ensure accuracy and professionalism. | open | Chat ¦ with Aman | Grammar errors can undermine the credibility of the brand and negatively impact user trust. | Conversion | Aman | High
Fix Broken CTAs | Identify and resolve the issue with the CTAs at the bottom of the product page to ensure they are functional and effective. | open | Chat ¦ with Aman | Broken CTAs can lead to lost sales and revenue opportunities. | Conversion | Aman | High
Finalize Mother's Day Gift Ideas | Select and finalize gift ideas for Mother's Day, focusing on thoughtful and comforting tea gifts. | open | Chat ¦ with Aman | To increase sales and customer satisfaction during the Mother's Day season. | AOV | Aman | High | Before Mother's Day
Create Email Subject Lines | Craft email subject lines for Mother's Day promotions, emphasizing comfort, care, and daily joy. | open | Chat ¦ with Manisha | To grab customers' attention and increase email open rates. | Acquisition | Manisha | Medium | Before sending Mother's Day emails
Finalize Email Campaign for First Flush Tea | Create and send an email campaign to customers about the First Flush tea, emphasizing its limited availability and freshness. | open | Chat ¦ with Aman | Increase sales and revenue by promoting a high-demand product. | Acquisition | Aman | High | Go Live
Review UK Consumer Emails | Review all UK consumer emails sent through Klaviyo, including drafts and real ones, up to 180 days, and document them in a single document. | open | Chat ¦ with Aman | To understand the current email marketing strategy and identify areas for improvement. | Retention | Aman | Medium
Review Cancellation Flow | Review the current cancellation flow and identify areas for improvement, including recommended projects and the flow of what happens. | open | Chat ¦ with Aman | To ensure a smooth customer experience and minimize cancellations. | Retention | Aman | Medium
Take Screenshots of Campaigns | Take screenshots of all relevant campaigns related to the cancellation flow and UK consumer emails. | open | Chat ¦ with Aman | To document the current state of email marketing campaigns. | Retention | Aman | Medium
Verify Hibiscus Rose Discount Consistency | Check why Hibiscus Rose is showing 40% off in mailer but 38% off on website globally and ensure consistency across all channels. | open | Chat ¦ with Anchit | Inconsistent discounts can lead to customer confusion and negatively impact sales. | Operations | Anchit | High
Retain Email Flow Documentation | Save the entire document containing all data and flow of emails currently live and running for all email flows. | open | Chat ¦ with Manisha | To maintain a record of current email flows and data for future reference and improvement. | Retention | Manisha | Medium
Integrate chatbot analytics with Vahdam India's existing metrics | Explore the possibility of integrating the chatbot's analytics with Vahdam India's existing metrics to gain a more comprehensive understanding of customer behavior and preferences. | open | Chat ¦ with users/110152155675645013355 | To better understand customer behavior and preferences, and to make data-driven decisions. | Acquisition | users/110152155675645013355 | Medium
Implement nudges on Vahdam India's PDP | Implement a similar nudge system on Vahdam India's PDP to encourage users to explore more products and increase average order value. | open | Chat ¦ with users/110152155675645013355 | To increase average order value and encourage users to explore more products. | AOV | users/110152155675645013355 | Medium
Develop a recommendation engine for Vahdam India's website | Develop a recommendation engine that suggests products to users based on their browsing history and preferences. | open | Chat ¦ with users/110152155675645013355 | To increase sales and improve customer satisfaction. | Conversion | users/110152155675645013355 | Medium
Analyze customer support queries to identify areas for improvement | Analyze customer support queries to identify areas where Vahdam India can improve its products, services, or customer support. | open | Chat ¦ with users/110152155675645013355 | To improve customer satisfaction and reduce support queries. | Retention | users/110152155675645013355 | Medium
Request for Quote (RFQ) | Send a formal request for quote to the potential agency, outlining Vahdam India's marketing needs and requirements. | open | Chat ¦ with Anchit Tandon | To get a clear understanding of the agency's services and fees. | Operations | Anchit Tandon | Medium
Discuss View-Only Access with Agency | Discuss the possibility of granting the agency view-only access to campaigns with the potential agency. | open | Chat ¦ with Aman | To ensure seamless collaboration and minimize potential issues. | Operations | Aman | Medium
Prepare Quotation Slab | Prepare a quotation slab for the agency's fees based on the ad spend bucket (5k-15k dollars). | open | Chat ¦ with Aman | To ensure transparency and clarity in the agency's fees. | Operations | Aman | Medium
Create Production-Ready HTML | Create production-ready HTML using content shared from Drive by Aman. | open | Chat ¦ with Aman | To ensure the content is ready for use in the production environment. | Team & Process | Aman | Medium
Set 2-hour timer | Set a timer for 2 hours to track the duration of the current conversation. | open | Chat ¦ with Aman | To keep track of the conversation duration and ensure the discussion stays focused. | Other | Aman | Medium | 2 hours
Host Images on Shopify | Host images on Shopify to improve website performance and reduce loading times. | open | Chat ¦ with Aman | Better image hosting will improve user experience and potentially increase conversion rates. | Operations | Aman | High
Host HTMLs on Shopify | Host HTMLs on Shopify to ensure consistency and ease of management. | open | Chat ¦ with Aman | Having HTMLs hosted on Shopify will simplify the process of updating and managing them. | Operations | Aman | Medium
Review UK Landing Pages | Review the Ashwagandha Coffee Landing Page and the Ashwagandha Coffee Starter Kit page on Vahdam's UK website to ensure they are optimized for conversion. | open | Chat ¦ with Aman | Chat ¦ DM | To improve conversion rates on the UK website. | Conversion | Aman | Medium
Update Canada-Specific Content | Update the Canada-specific content on Vahdam's website to ensure it is accurate and relevant to the Canadian market. | open | Chat ¦ with Manisha | Chat ¦ DM | To improve the user experience for Canadian customers. | Acquisition | Manisha | Medium
Review Nutrition Support Pages | Review the Nutrition Support pages on Vahdam's website to ensure they are informative and helpful to customers. | open | Chat ¦ with Arihant | Chat ¦ DM | To improve customer engagement and retention. | Retention | Arihant | Low
Provide UK Data in Specified Format | Extract and provide UK data from 01-Dec-2025 to 31-Mar-2026 in the specified format. | open | Chat ¦ with Aman | Chat ¦ DM | Anchit needs this data for analysis and decision-making. | Operations | Aman | High | As soon as possible
Prepare Price Parity Sheet | Create a comprehensive price parity sheet comparing Vahdam India's prices across all marketplaces, including Shopify, Amazon US/IN, and other platforms. | open | Chat ¦ with Anchit (Self) | Chat ¦ DM with users/101892413922856052375 | To ensure price parity and maintain a competitive edge across all marketplaces. | Operations | Anchit (Self) | High
Update on Gorilla sheet | Get an update on the current status of the Gorilla sheet. | open | Chat ¦ with users/101892413922856052375 | Chat ¦ DM with users/101892413922856052375 | Need to understand the current state of the Gorilla sheet to plan further. | Other | users/101892413922856052375 | Medium
Research Amazon Pricing | Compare Vahdam India's prices with Amazon's prices for similar products to identify any discrepancies. | open | Chat ¦ with Anchit (Self) | Chat ¦ DM with users/101892413922856052375 | Understanding price differences can help inform pricing strategies and improve competitiveness. | Operations | Anchit (Self) | Medium
Complete App Creation | Anshith needs to finish creating his app by the weekend. | open | Meeting ¦ speaker Anchit | Meeting ¦ voice memo by Anchit (Self) | App creation is a priority to move forward with new features and revenue growth. | Team & Process | Anshith | High | by the weekend
Review Email List and Body | Review the email list and body sent by the user and take necessary actions. | open | Chat ¦ with Anchit (Self) | Chat ¦ DM with users/112363631041538884730 | Reviewing the email list and body is necessary to understand the context and requirements of the mail. | Other | Anchit (Self) | Medium
Follow up on user query | Respond to the user's query in the DM. | open | Chat ¦ with Anchit (Self) | Chat ¦ DM with users/112363631041538884730 | Address the user's concern to provide a good customer experience. | Operations | Anchit (Self) | High
Check Something | The recipient needs to check something as requested by Anchit. | open | Chat ¦ with users/112363631041538884730 | Chat ¦ DM with users/112363631041538884730 | Anchit needs this checked to move forward. | Other | users/112363631041538884730 | Medium
Send requested file | Send the requested file to the user today. | open | Chat ¦ with Anchit (Self) | Chat ¦ DM with users/112363631041538884730 | Meet the user's request to send the file today. | Other | Anchit (Self) | High | Today
Share the item by night | Share the item with the recipient by the end of the day. | open | Chat ¦ with Anchit (Self) | Chat ¦ DM with users/112363631041538884730 | The recipient is waiting for the item to be shared. | Other | Anchit (Self) | Medium | by night
Follow up on salary account opening | Reach out to the bank to inquire about the process and requirements for opening a salary account. | open | Chat ¦ with Subham | Chat ¦ DM | This will help Subham understand the process and requirements for opening a salary account. | Other | Subham | Low
Schedule Meeting | Schedule a meeting with Aman to discuss the same topic. | open | Chat ¦ with Aman | Chat ¦ DM | Need to discuss something with Aman. | Team & Process | Aman | Medium | As soon as possible
Update on Current Status | Subham to provide an update on the current status of the topic Anchit inquired about. | open | Chat ¦ with Subham | Chat ¦ DM | Anchit needs to stay informed about the topic. | Other | Subham | Medium
Provide VTAdmin account password | Share the admin account password (VTAdmin) with Shahzad to help with installing Claude. | open | Chat ¦ with Shehzad | Chat ¦ DM | Installing Claude requires the admin account password to proceed. | Team & Process | Shahzad | High
Provide vtadmin password | Shehzad needs to share the vtadmin password with Anchit. | open | Chat ¦ with Shehzad | Chat ¦ DM | Anchit needs access to the vtadmin password for work. | Operations | Shehzad | Medium
Create Automated Tracker Project | Develop an automated project to track and check various aspects of the business. | open | Meeting | Meeting ¦ voice memo by Anchit (Self) | To improve efficiency and reduce manual errors. | Operations |  | Medium

## Tasks From Discussions
Task Heading | Task Description | Status | Source | Why We're Doing This | Growth Pillar | SPOC | Priority | Go Live | Remarks
Check Caption on Amazon | Verify if the specified range is available on Amazon to ensure the caption is accurate. | open | Chat ¦ with Aman | Accurate product information is crucial for customer satisfaction and trust. | Operations | Aman | Medium
Create Bundle Link | Create a link for the bundle that is missing images, and share it with Anchit. | open | Chat ¦ with Manisha | Missing images are blocking the bundle's visibility, and having a link will help Anchit move forward. | Operations | Manisha | High
Work with Aman on Klaviyo Integration | Collaborate with Aman to figure out Klaviyo integration and its requirements. | open | Chat ¦ with Anchit Tandon | Klaviyo integration is crucial for retention via email/SMS/WhatsApp. | Retention | Anchit Tandon | High
Review Mailer Creation Document | Review the document with feedbacks for mailer creation and ensure it's ready for today. | open | Chat ¦ with Anchit | To ensure the mailer creation is done correctly and on time. | Operations | Anchit | High | Today
Send 1st mailer | Send the first mailer as per the calendar sheet to subscribers. | open | Chat ¦ with Aman | To maintain a consistent gifting calendar and keep subscribers engaged. | Retention | Aman | Medium | As per calendar sheet
Fix Product Page Alignment | Ensure that the product descriptions are evenly spaced and do not break the alignment on the product page. | open | Chat ¦ with Aman | A cluttered product page can negatively impact user experience and conversion rates. | Conversion | Aman | High
Correct Grammar in Product Selection | Review and correct the grammar in the product selection percentage (currently 58%) to ensure accuracy and professionalism. | open | Chat ¦ with Aman | Grammar errors can undermine the credibility of the brand and negatively impact user trust. | Conversion | Aman | High
Fix Broken CTAs | Identify and resolve the issue with the CTAs at the bottom of the product page to ensure they are functional and effective. | open | Chat ¦ with Aman | Broken CTAs can lead to lost sales and revenue opportunities. | Conversion | Aman | High
Finalize Mother's Day Gift Ideas | Select and finalize gift ideas for Mother's Day, focusing on thoughtful and comforting tea gifts. | open | Chat ¦ with Aman | To increase sales and customer satisfaction during the Mother's Day season. | AOV | Aman | High | Before Mother's Day
Create Email Subject Lines | Craft email subject lines for Mother's Day promotions, emphasizing comfort, care, and daily joy. | open | Chat ¦ with Manisha | To grab customers' attention and increase email open rates. | Acquisition | Manisha | Medium | Before sending Mother's Day emails
Finalize Email Campaign for First Flush Tea | Create and send an email campaign to customers about the First Flush tea, emphasizing its limited availability and freshness. | open | Chat ¦ with Aman | Increase sales and revenue by promoting a high-demand product. | Acquisition | Aman | High | Go Live
Review UK Consumer Emails | Review all UK consumer emails sent through Klaviyo, including drafts and real ones, up to 180 days, and document them in a single document. | open | Chat ¦ with Aman | To understand the current email marketing strategy and identify areas for improvement. | Retention | Aman | Medium
Review Cancellation Flow | Review the current cancellation flow and identify areas for improvement, including recommended projects and the flow of what happens. | open | Chat ¦ with Aman | To ensure a smooth customer experience and minimize cancellations. | Retention | Aman | Medium
Take Screenshots of Campaigns | Take screenshots of all relevant campaigns related to the cancellation flow and UK consumer emails. | open | Chat ¦ with Aman | To document the current state of email marketing campaigns. | Retention | Aman | Medium
Verify Hibiscus Rose Discount Consistency | Check why Hibiscus Rose is showing 40% off in mailer but 38% off on website globally and ensure consistency across all channels. | open | Chat ¦ with Anchit | Inconsistent discounts can lead to customer confusion and negatively impact sales. | Operations | Anchit | High
Retain Email Flow Documentation | Save the entire document containing all data and flow of emails currently live and running for all email flows. | open | Chat ¦ with Manisha | To maintain a record of current email flows and data for future reference and improvement. | Retention | Manisha | Medium
Integrate chatbot analytics with Vahdam India's existing metrics | Explore the possibility of integrating the chatbot's analytics with Vahdam India's existing metrics to gain a more comprehensive understanding of customer behavior and preferences. | open | Chat ¦ with users/110152155675645013355 | To better understand customer behavior and preferences, and to make data-driven decisions. | Acquisition | users/110152155675645013355 | Medium
Implement nudges on Vahdam India's PDP | Implement a similar nudge system on Vahdam India's PDP to encourage users to explore more products and increase average order value. | open | Chat ¦ with users/110152155675645013355 | To increase average order value and encourage users to explore more products. | AOV | users/110152155675645013355 | Medium
Develop a recommendation engine for Vahdam India's website | Develop a recommendation engine that suggests products to users based on their browsing history and preferences. | open | Chat ¦ with users/110152155675645013355 | To increase sales and improve customer satisfaction. | Conversion | users/110152155675645013355 | Medium
Analyze customer support queries to identify areas for improvement | Analyze customer support queries to identify areas where Vahdam India can improve its products, services, or customer support. | open | Chat ¦ with users/110152155675645013355 | To improve customer satisfaction and reduce support queries. | Retention | users/110152155675645013355 | Medium
Request for Quote (RFQ) | Send a formal request for quote to the potential agency, outlining Vahdam India's marketing needs and requirements. | open | Chat ¦ with Anchit Tandon | To get a clear understanding of the agency's services and fees. | Operations | Anchit Tandon | Medium
Discuss View-Only Access with Agency | Discuss the possibility of granting the agency view-only access to campaigns with the potential agency. | open | Chat ¦ with Aman | To ensure seamless collaboration and minimize potential issues. | Operations | Aman | Medium
Prepare Quotation Slab | Prepare a quotation slab for the agency's fees based on the ad spend bucket (5k-15k dollars). | open | Chat ¦ with Aman | To ensure transparency and clarity in the agency's fees. | Operations | Aman | Medium
Create Production-Ready HTML | Create production-ready HTML using content shared from Drive by Aman. | open | Chat ¦ with Aman | To ensure the content is ready for use in the production environment. | Team & Process | Aman | Medium
Set 2-hour timer | Set a timer for 2 hours to track the duration of the current conversation. | open | Chat ¦ with Aman | To keep track of the conversation duration and ensure the discussion stays focused. | Other | Aman | Medium | 2 hours
Host Images on Shopify | Host images on Shopify to improve website performance and reduce loading times. | open | Chat ¦ with Aman | Better image hosting will improve user experience and potentially increase conversion rates. | Operations | Aman | High
Host HTMLs on Shopify | Host HTMLs on Shopify to ensure consistency and ease of management. | open | Chat ¦ with Aman | Having HTMLs hosted on Shopify will simplify the process of updating and managing them. | Operations | Aman | Medium
Review UK Landing Pages | Review the Ashwagandha Coffee Landing Page and the Ashwagandha Coffee Starter Kit page on Vahdam's UK website to ensure they are optimized for conversion. | open | Chat ¦ with Aman | Chat ¦ DM | To improve conversion rates on the UK website. | Conversion | Aman | Medium
Update Canada-Specific Content | Update the Canada-specific content on Vahdam's website to ensure it is accurate and relevant to the Canadian market. | open | Chat ¦ with Manisha | Chat ¦ DM | To improve the user experience for Canadian customers. | Acquisition | Manisha | Medium
Review Nutrition Support Pages | Review the Nutrition Support pages on Vahdam's website to ensure they are informative and helpful to customers. | open | Chat ¦ with Arihant | Chat ¦ DM | To improve customer engagement and retention. | Retention | Arihant | Low
Provide UK Data in Specified Format | Extract and provide UK data from 01-Dec-2025 to 31-Mar-2026 in the specified format. | open | Chat ¦ with Aman | Chat ¦ DM | Anchit needs this data for analysis and decision-making. | Operations | Aman | High | As soon as possible
Prepare Price Parity Sheet | Create a comprehensive price parity sheet comparing Vahdam India's prices across all marketplaces, including Shopify, Amazon US/IN, and other platforms. | open | Chat ¦ with Anchit (Self) | Chat ¦ DM with users/101892413922856052375 | To ensure price parity and maintain a competitive edge across all marketplaces. | Operations | Anchit (Self) | High
Update on Gorilla sheet | Get an update on the current status of the Gorilla sheet. | open | Chat ¦ with users/101892413922856052375 | Chat ¦ DM with users/101892413922856052375 | Need to understand the current state of the Gorilla sheet to plan further. | Other | users/101892413922856052375 | Medium
Research Amazon Pricing | Compare Vahdam India's prices with Amazon's prices for similar products to identify any discrepancies. | open | Chat ¦ with Anchit (Self) | Chat ¦ DM with users/101892413922856052375 | Understanding price differences can help inform pricing strategies and improve competitiveness. | Operations | Anchit (Self) | Medium
Complete App Creation | Anshith needs to finish creating his app by the weekend. | open | Meeting ¦ speaker Anchit | Meeting ¦ voice memo by Anchit (Self) | App creation is a priority to move forward with new features and revenue growth. | Team & Process | Anshith | High | by the weekend
Review Email List and Body | Review the email list and body sent by the user and take necessary actions. | open | Chat ¦ with Anchit (Self) | Chat ¦ DM with users/112363631041538884730 | Reviewing the email list and body is necessary to understand the context and requirements of the mail. | Other | Anchit (Self) | Medium
Follow up on user query | Respond to the user's query in the DM. | open | Chat ¦ with Anchit (Self) | Chat ¦ DM with users/112363631041538884730 | Address the user's concern to provide a good customer experience. | Operations | Anchit (Self) | High
Check Something | The recipient needs to check something as requested by Anchit. | open | Chat ¦ with users/112363631041538884730 | Chat ¦ DM with users/112363631041538884730 | Anchit needs this checked to move forward. | Other | users/112363631041538884730 | Medium
Send requested file | Send the requested file to the user today. | open | Chat ¦ with Anchit (Self) | Chat ¦ DM with users/112363631041538884730 | Meet the user's request to send the file today. | Other | Anchit (Self) | High | Today
Share the item by night | Share the item with the recipient by the end of the day. | open | Chat ¦ with Anchit (Self) | Chat ¦ DM with users/112363631041538884730 | The recipient is waiting for the item to be shared. | Other | Anchit (Self) | Medium | by night
Follow up on salary account opening | Reach out to the bank to inquire about the process and requirements for opening a salary account. | open | Chat ¦ with Subham | Chat ¦ DM | This will help Subham understand the process and requirements for opening a salary account. | Other | Subham | Low
Schedule Meeting | Schedule a meeting with Aman to discuss the same topic. | open | Chat ¦ with Aman | Chat ¦ DM | Need to discuss something with Aman. | Team & Process | Aman | Medium | As soon as possible
Update on Current Status | Subham to provide an update on the current status of the topic Anchit inquired about. | open | Chat ¦ with Subham | Chat ¦ DM | Anchit needs to stay informed about the topic. | Other | Subham | Medium
Provide VTAdmin account password | Share the admin account password (VTAdmin) with Shahzad to help with installing Claude. | open | Chat ¦ with Shehzad | Chat ¦ DM | Installing Claude requires the admin account password to proceed. | Team & Process | Shahzad | High
Provide vtadmin password | Shehzad needs to share the vtadmin password with Anchit. | open | Chat ¦ with Shehzad | Chat ¦ DM | Anchit needs access to the vtadmin password for work. | Operations | Shehzad | Medium
Create Automated Tracker Project | Develop an automated project to track and check various aspects of the business. | open | Meeting | Meeting ¦ voice memo by Anchit (Self) | To improve efficiency and reduce manual errors. | Operations |  | Medium
Create Automated Tracker Project | Develop an automated project to track and check various aspects of the business. | open | Meeting | Meeting ¦ voice memo by Anchit (Self) | To improve efficiency and reduce manual errors. | Operations |  | Medium

## Tasks From Mails
Task Heading | Task Description | Status | Source | Why We're Doing This | Growth Pillar | SPOC | Priority | Go Live | Remarks